2016 Edition

SE-685

GENERAL CONDITIONS TO CONSTRUCTION SERVICES INDEFINITE DELIVERY CONTRACT

AGENCY:

PROJECT NAME:

PROJECT NUMBER:

CONTRACTOR:

#### GENERAL INFORMATION

1.1 Contract Documents: The Contract Documents are identified in the Construction Services Indefinite Delivery Contract (the “Contract”). The Contract can only be modified by written agreement signed by both the Agency and the Contractor. The Contract Documents do not create a contractual relationship between the Contractor and any separate Contractor having a contract with the Agency; between the Agency and any subcontractor to the Contractor of any tier; or between any persons or entities other than the Agency and the Contractor.

1.2 Delivery Order: A Delivery Order is a written order issued by the Agency to the Contractor under the terms and conditions of the Contract, directing the Contractor to perform the work described therein. The Agency shall issue the Delivery Order on the SE-690, Construction Services IDC Delivery Order.

1.3 Contractor shall not incur any expense chargeable to the Agency on or about the work of any Delivery Order assigned to this contract until the Delivery Order has been awarded and fully executed by both the Agency and the Contractor.

1.4 The Contract is subject to strict expenditure and term limits set forth in State Law at S.C. Code Ann. § 11-35-3310 and further explained in the Manual for Planning and Execution of State Permanent Improvements, Part II (the “Manual”). Any modification to the Contract purporting to exceed these strict limits are null and void. The limits applicable to this Contract are set forth in Part I of the Invitation for Indefinite Delivery of Construction Services.

1.5 The Work: As used herein, the “Work” means any work required of or performed by the Contractor pursuant to each and every Delivery Order issued by the Agency under this Contract.

1. AGENCY

2.1 The term “Agency” means the Agency or the Agency’s Representative.

2.2 Representative: The Agency’s representative designated in Part G(1) of the agreement shall have the authority to bind the Agency with respect to all matters regarding the Contract and requiring the Agency’s approval or authorization.

2.3 Information to the Contractor: The Agency shall furnish, with reasonable promptness, information requested by the Contractor that is necessary for the performance of the Contract Services and under the Agency’s control. Any information or documentation provided by the Agency to the Contractor relating to the Project or Site is provided only for the convenience of the Contractor. The Agency makes no representation or warranty to as to the sufficiency, completeness, or accuracy of such information.

2.4 Utility Access and Use:

If this box is checked, the Agency shall allow the Contractor to use reasonable quantities of water and electricity for construction purposes without charge, as long as these utilities are available and in close proximity to the Work area. Contractor shall be conscientious in controlling excessive or frivolous use of the utilities or the Agency may charge the Contractor for wasteful usage.

2.5 Sanitary Facilities: *(Agency, check box that applies to this contract)*

The Contractor may use those sanitary facilities designated by the Agency in each Delivery Order as available for use.

The Contractor may not use the Agency’s sanitary facilities. The Contractor shall provide sanitary facilities at the job site and maintain same in a clean and sanitary condition for the use of its employees and employees of its subcontractors for the duration of construction. The sanitary facilities shall conform to the requirements of the South Carolina Department of Health and Environmental Control.

2.6 Permits, Assessments, and Easements: The Agency shall secure and pay for all building permits, zoning permits, assessments, and easements except as required by any Delivery Order issued under the terms of the contract

2.7 Agency’s Architect-Engineer (A/E): The Agency may retain an independent A/E to prepare design documents for the work of a specific Delivery Order. In such event, the A/E will be a representative of the Agency during the performance of such work through final completion of such work. In the absence of an independent A/E, the Agency will assign one of its employees to act as A/E for the work of a particular Delivery Order. The Contractor shall cooperate with the A/E in the performance of its duties. The A/E will perform the following duties:

a. The A/E will make periodic visits to the site during contract administration to become familiar with the progress of the work and to determine if the work is generally progressing in accordance with the contract documents.

b. The A/E will make recommendations to the Agency as to acceptance or rejection of the work and, upon the Agency’s concurrence, communicate the acceptance or rejection of the work to the Contractor.

c. The A/E will review and approve or reject shop drawings and samples submitted by the Contractor showing details/finishes of the work proposed to be installed.

d. The decision of the A/E in all matters relating to design and interpretation of contract documents shall, subject to the provisions of Part 5 (Dispute Resolution) be final.

e. The A/E will not be responsible for construction means, methods, techniques, procedures and safety measures in the performance of the work nor acts or omissions of the Contractor, subcontractors or any other entity performing work on the site.

f. The A/E will review requests for payment, and make recommendations to the Agency for approval or rejection of all or part of the request.

g. The A/E will prepare change orders or change directives for review and approval by the Agency.

2.8 Construction by Agency: The Agency may do work with its own forces or award separate contracts for work on the same project as may be awarded by Delivery Order under this contract. The Contractor shall allow access to the site by the Agency’s work force or separate Contractor(s), and shall cooperate in coordinating the progress of the work with the Agency. The Agency shall have the responsibility to coordinate the activities of the various Contractors working at the project location.

1. CONTRACTOR

3.1 The term “Contractor” means the Contractor or the Contractor’s Representative.

3.2 Representative: The Contractor’s representative designated in Part G(2) of the Agreement shall have the authority to bind the Contractor with respect to all matters regarding the Contract and requiring the Contractor’s approval or authorization.

3.3 Supervision and Performance of the Work: The Contractor shall supervise, perform, and direct the Work, using the professional skill, care, and attention reasonably required for similar projects. The Contractor shall be solely responsible for and have control over means, methods, techniques, sequences, and procedures and for coordinating the Work, unless the Contract Documents give other specific instructions concerning these matters. The Contractor agrees to faithfully and fully perform the terms of this Contract, and any Delivery Order issued under this Contract and shall complete the Work in accordance with the Contract Documents and deliver the Work to the Agency free and clear of all liens and claims. The Contractor shall, at all times during the progress the Work, employ enough skilled workers and have on hand and maintain an adequate supply of materials and equipment to complete the Work in accordance with the construction schedules agreed to in applicable Delivery Orders.

3.4 Employee Discipline: The Contractor shall enforce discipline and good order among the Contractor’s and subcontractors’ employees, and other persons carrying out the Work. Contractor shall be responsible to the Agency for acts and omissions of the Contractor’s employees, subcontractors and their agents and employees, and other persons or entities performing portions of the Work for, or on behalf of, the Contractor or any of its Subcontractors.

3.5 Safety: The Contractor shall comply with all federal and state work site safety requirements and shall be responsible for initiating, maintaining, and supervising reasonable safety precautions and programs in connection with the performance of the Contract Services. The Contractor shall take reasonable precautions for safety of, and shall provide reasonable and appropriate protection to prevent damage, injury or loss to (1) employees on the Work and other persons who may be affected thereby; (2) the Work and materials and equipment to be incorporated therein; and (3) other property at the site of the Work or adjacent thereto.

3.6 Waste Materials and Rubbish: The Contractor shall keep the premises and surrounding areas free from accumulation of waste materials or rubbish caused by the Work. Upon Final Acceptance of the Work, the Contractor shall, to the Agency’s satisfaction, remove from and about the site, all waste materials, rubbish, surplus material, and Contractor’s tools, equipment, machinery.

3.7 Recycling: The Contractor shall give preference to the use of products containing recycled content in the performance of the Work. The Contractor shall cooperate with any recycling program established for the site of the work of any Delivery Order or available through the state or a political subdivision of the state.

3.8 Access to the Work: The Contractor shall provide the Agency with unrestricted access to the Work in preparation and progress wherever located.

3.9 Use of Site: The Contractor shall confine its operations to the portions of the site identified in each Delivery Order or otherwise approved by the Agency, and shall not unreasonably encumber the portions of the site used for the Work with materials, equipment, or similar items. The Contractor and all subcontractors shall use only such entrances to the Site as are designated by the Agency. During occupied hours, Contractor shall limit construction operations to methods and procedures that do not adversely affect the environment of occupied spaces within the Site, including but not limited to creating noise, odors, air pollution, ambient discomfort, or poor lighting.

3.10 Correction of the Work:

3.10.1 The Agency shall have the right and authority to reject Work that does not conform to the Contract Documents. The Contractor shall promptly correct Work rejected by the Agency for failing to conform to the requirements of the Contract Documents, whether or not fabricated, installed or completed. The provisions of this Section 3.10 apply to Work done by subcontractors as well as to Work done by direct employees of the Contractor.

3.10.2 If the Contractor fails to correct the Work, or any portion thereof, that is not in accordance with the requirements of the Contract Documents or fails to carry out Work or provide information in accordance with the Contract Documents, the Agency may make written demand upon the Contractor to cure its defaults within seven days. Within seven days after receipt of the Agency’s demand, the Contractor shall cure its defaults unless the default is such that it is not capable of cure within seven days. If the default is such that it is not capable of cure within seven days, the Contractor shall reach an agreement with the Agency on a plan to cure its defaults within five days after receipt of the Agency’s demand. The Contractor shall commence and diligently and continuously pursue the cure of such defaults in accordance with the agreed plan. If the Contractor fails to cure its defaults as heretofore provided, the Agency may order the Contractor, in writing, to stop the Work, or any portion thereof, until the Contractor has eliminated the cause for such order or has provided the Agency with a plan for corrective action acceptable to the Agency. The right of the Agency to stop the Work shall not give rise to a duty on the part of the Agency to exercise this right for the benefit of the Contractor or any other person or entity.

3.10.3 Correction after Substantial Completion: If, within one year after the date of Substantial Completion of the Work, any of the Work is found to be not in accordance with the requirements of the Contract Documents, the Contractor shall correct it promptly after receipt of written notice from the Agency to do so. The Contractor’s obligation set forth in this Part 3.10.3 is in addition to the Contractor’s obligations under Part 3.12.

3.10.4 Nothing contained in this Part 3.10 shall be construed to establish a period of limitation with respect to other obligations the Contractor has under the Contract Documents. Establishment of such time period as described in this Section 3.10 relates only to the specific obligation of the Contractor to correct the Work, and has no relationship to the time within which the obligation to comply with the Contract Documents may be sought to be enforced, nor to the time within which proceedings may be commenced to establish the Contractor’s liability with respect to the Contractor’s obligations other than specifically to correct the Work.

3.11 Manufacturers’ Warranties: At Final Acceptance of the Work, the Contractor shall furnish the Agency two original complete sets of all manufacturers’ warranties, guarantees, parts lists, and literature applicable to equipment, systems, fittings, and furnishings included in the Work (collectively referred to as “*Manufacturers’ Warranties*”), completed in favor of the Agency. These Manufacturers’ Warranties are in addition to and not in lieu of the Contractor’s warranty set forth in Part 3.12, and the Agency is entitled to look to the Contractor for remedy in all cases where the Contractor’s warranty applies regardless of whether a Manufacturer’s Warranty also applies. The Agency shall acknowledge receipt of the sets of Manufacturers’ Warranties on the set itself, and the Contractor shall cause six (6) copies of an acknowledged set to be made and furnished to the Agency. All Manufacturers’ Warranties will be for applicable periods and contain terms not less favorable to the Agency than those terms that are standard for the applicable industries, and will either be issued in the first instance in the name of and for benefit of the Agency, or be in a freely assignable form and be assigned to the Agency without limitations.

3.12 Contractor Warranty: The Contractor warrants to the Agency that materials and equipment furnished under the Contract will be of good quality and new unless otherwise required or permitted by the Contract Documents, that the Work will be free from faults and defects not inherent in the quality required or permitted, that the materials, equipment and Work will conform with the requirements of the Contract Documents, and that the Work will be free from any encumbrances, liens, security interests, or other defects in title upon conveyance of title to the Agency. The Contractor’s warranty excludes remedy for damage or defect to the extent caused by (i) abuse by anyone other than the Contractor or those for whose acts the Contractor is responsible, (ii) modifications not approved or executed by the Contractor or subcontractors, (iii) improper or insufficient maintenance or operation not the fault of the Contractor or those for whose acts the Contractor is responsible, or (iv) normal wear and tear under normal usage. If required by the Agency, the Contractor shall furnish satisfactory evidence as to the kind and quality of materials and equipment and the recommended maintenance thereto to meet the requirements of this Part.

3.13 After completion of the Work but no later than the date of Substantial Completion, the Contractor shall submit operation and maintenance manuals, recommended spare parts lists, and copies of all warranties to the Agency. As-Built drawings shall be submitted no later than the Final Completion Date.

3.14 Compliance with Law:

3.14.1 The Contractor shall comply with and give all notices required by federal, state, county, and municipal laws, ordinances, regulations, and orders bearing on the performance by the Contractor of the duties or responsibilities under this Contract.

3.14.2 The Contractor shall promptly remedy any violation of any such law, ordinance, rule, regulation, or order that comes to its attention to the extent that the same results from its performance of the Work. The Contractor shall promptly, and in no event later than the close of the next business day following receipt, give notice to the Agency by telephone, with confirmation in writing, of receipt by the Contractor of any information relating to violations of laws, ordinances, rules, regulations, and orders.

3.15 Subcontractors:

3.15.1 The Contractor shall furnish in writing to the Agency for its approval the names of the subcontractors to whom the Contractor plans to award any portion of the Contract Services.

3.15.2 Contracts between the Contractor and subcontractors shall require each subcontractor, to the extent of the Contract Services to be performed by the subcontractor, to be bound to the Contractor by the terms of the Contract Documents, and to assume toward the Contractor all the obligations and responsibilities which the Contractor, by the Contract Documents, assumes toward the Agency.

3.15.3 The Contractor shall be responsible to the Agency for acts and omissions of the subcontractors, their agents and employees, and any other persons performing portions of the Contract Services, to the same extent as the acts or omissions of the Contractor hereunder.

3.15.4 The Iran Divestment Act List is a list published by the State Fiscal Accountability Authority pursuant to Section 11-57-310 that identifies persons engaged in investment activities in Iran. The list is available at the following URL: [http://procurement.sc.gov/PS/PS-iran-divestment.phtm(.)](http://procurement.sc.gov/PS/PS-iran-divestment.phtm%20) Consistent with Section 11-57-330(B), the Contractor shall not contract with any person to perform a part of the Work, if, at the time you enter into the subcontract, that person is on the then-current version of the Iran Divestment Act List.

3.16 Publicity: Contractor shall not publish any comments or quotes by State employees, or include the State in either news releases or a published list of agencies, without the prior written approval of the Agency.

3.17 Indemnification

3.17.1 To the fullest extent permitted by law, the Contractor shall indemnify and hold harmless the Agency and the Agency’s agents and employees from and against claims, damages, losses and expenses, including, but not limited to, reasonable attorney’s fees, arising out of or resulting from performance of the work of a Delivery Order, provided that such claim, damage, loss or expense is attributable to bodily injury, sickness, disease or death, or to injury to or destruction of tangible property (other than the Work itself), including loss of use resulting therefrom, but only to the extent caused by negligent acts or omissions of the Contractor, a subcontractor, anyone directly or indirectly employed by them or anyone for whose acts they may be liable, regardless of whether or not such claim, damage, loss or expense is caused in part by a party indemnified hereunder.

3.17.2 In claims against any person or entity indemnified under Part 3.17.1 by an employee of the Contractor, a subcontractor, anyone directly or indirectly employed by them or anyone for whose acts they may be liable, the indemnification obligation under this Part 3.17 shall not be limited by a limitation on amount or type of damages, compensation or benefits payable by or for Contractor or a subcontractor under workers’ or workmen’s compensation acts, disability benefit acts, or other employee benefit acts.

3.18 Insurance

3.18.1 Commercial General Liability, Business Automobile Liability, and Worker’s Compensation: The Contractor shall purchase from and maintain, in a company or companies lawfully authorized to do business in South Carolina, such insurance as will protect Contractor from claims set forth below, which may arise out of or result from Contractor’s operations and completed operations under the Contract and for which the Contractor may be legally liable, whether such operations be by the Contractor or by a subcontractor or by anyone directly or indirectly employed by any of them, or by anyone for whose acts any of them may be liable:

(a) claims under workers’ compensation, disability benefit and other similar employee benefit acts which are applicable to the Work to be performed;

(b) claims for damages because of bodily injury, occupational sickness or disease, or death of the Contractor’s employees;

(c) claims for damages because of bodily injury, sickness or disease, or death of any person other than the Contractor’s employees;

(d) claims for damages insured by usual personal injury liability coverage;

(e) claims for damages, other than to the Work itself, because of injury to or destruction of tangible property, including loss of use resulting therefrom;

(f) claims for damages because of bodily injury, death of a person or property damage arising out of ownership, maintenance or use of a motor vehicle;

(g) claims for bodily injury or property damage arising out of completed operations; and

(h) claims involving contractual liability insurance applicable to the Contractor’s obligations under Part 3.17, Indemnification.

3.18.1.1 The insurance required by Part 3.18.1 shall be written for not less than the limits of liability specified below or required by law, whichever is greater. Coverage shall be written on an occurrence basis and shall be maintained without interruption from the date of commencement of the Work until date of final payment and termination of any coverage required to be maintained after final payment and, with respect to the Contractor’s completed operations coverage, until the expiration of the period for correction of Work set forth in Part 3.10 or for such other period for maintenance of completed operations coverage as specified in the Contract Documents.

(a) COMMERCIAL GENERAL LIABILITY:

(1) General Aggregate (per project) $1,000,000

(2) Products/Completed Operations $1,000,000

(3) Personal and Advertising Injury $1,000,000

(4) Each Occurrence $1,000,000

(5) Fire Damage (Any one fire) $50,000

(6) Medical Expense (Any one person) $5,000

(b) BUSINESS AUTO LIABILITY (including All Owned, Non-owned, and Hired Vehicles):

(1) Combined Single Limit $1,000,000 OR

(2) Bodily Injury & Property Damage (each) $750,000

(c) WORKER’S COMPENSATION:

(1) State Statutory

(2) Employers Liability $100,000 Per Acc.

$500,000 Disease, Policy Limit

$100,000 Disease, Each Employee

In lieu of separate insurance policies for Commercial General Liability, Business Auto Liability, and Employers Liability, the Contractor may provide an umbrella policy meeting or exceeding all coverage requirements set forth in this Part 3.18.1. The umbrella policy limits shall not be less than $5,000,000.

3.18.1.2 Prior to commencement of the Work, and thereafter upon replacement of each required policy of insurance, Contractor shall provide to the Agency a written endorsement to the Contractor’s general liability insurance policy that:

1. names the Agency as an additional insured for claims caused in whole or in part by the Contractor’s negligent acts or omissions during the Contractor’s operations;
2. provides that no material alteration, cancellation, non-renewal, or expiration of the coverage contained in such policy shall have effect unless all additional insured have been given at least ten (10) days prior written notice of cancellation for non-payment of premiums and thirty (30) days prior written notice of cancellation for any other reason; and
3. provides that the Contractor’s liability insurance policy shall be primary, with any liability insurance of the Agency as secondary and noncontributory.

3.18.1.3 Before commencement of the Work, and thereafter upon renewal or replacement of each required policy of insurance, Contractor shall provide to the Agency a signed, original certificate of liability insurance (ACORD 25). Consistent with this Part 3.18.1, the certificate shall identify the types of insurance, state the limits of liability for each type of coverage, name the Agency as Certificate Holder, provide that the general aggregate limit applies per project, and provide that coverage is written on an occurrence basis. Both the certificates and the endorsements must be received directly from either the Contractor’s insurance agent or the insurance company. An additional certificate evidencing continuation of liability coverage, including coverage for completed operations, naming the Agency as an additional insured for claims made under the Contractor’s completed operations, and otherwise meeting the above requirements, shall be submitted with the Contractor’s final request for payment for the Work and thereafter upon renewal or replacement of such coverage until the expiration of the time required by Part 3.18.1. Information concerning reduction of coverage on account of revised limits or claims paid under the General Aggregate, or both, shall be furnished by the Contractor with reasonable promptness.

3.18.1.4 A failure by the Agency either (i) to demand a certificate of insurance or written endorsement required by Part 3.18.1, or (ii) to reject a certificate or endorsement on the grounds that it fails to comply with Part 3.18.1, shall not be considered a waiver of Contractor’s obligations to obtain the required insurance.

3.18.2 Property Insurance:

3.18.2.1 Builder’s Risk Insurance: Unless otherwise specified in the Delivery Order, at the time of execution of a Delivery Order and before commencing work under that Delivery Order, Contractor shall purchase property insurance written on a builder's risk "all risk" or equivalent policy form on a replacement cost basis. Contractor shall maintain such property insurance until the Agency has made final payment for the work of the Delivery Order or until no person or entity other than the Agency has an insurable interest in the property required by this Paragraph 3.18.2 to be covered, whichever is later. This insurance shall include and be in an amount sufficient to cover at all times during the performance of the work of the Delivery Order, the interests of the Contractor, Subcontractors and Sub-subcontractors in the Delivery Order Project. The property insurance shall include, without limitation, insurance against the perils of fire (with extended coverage) and physical loss or damage including, without duplication of coverage, theft, vandalism, malicious mischief, collapse, earthquake, flood, windstorm, false work, testing and startup, temporary buildings and debris removal including demolition occasioned by enforcement of any applicable legal requirements, and shall cover reasonable compensation for Architect's and Contractor's services and expenses required as a result of such insured loss.

3.18.2.2 Equipment Breakdown Insurance: In the event the Contractor installs and runs and/or operates (whether for testing or other purposes) heating, air conditioning, and electrical machinery and equipment, the Contractor shall purchase and maintain equipment breakdown (boiler and machinery) insurance, which shall specifically cover such objects during installation and until final acceptance by the Agency. This insurance shall include interests of the Agency, Contractor, and subcontractors at any tier in the Work, and the Agency and Contractor shall both be named insured.

3.18.2.3 Before an exposure to loss may occur, the Contractor shall file with the Agency a copy of each policy that includes insurance coverage required by this Part 3.18.2. Each policy shall contain all generally applicable conditions, definitions, exclusions and endorsements related to this Project.

3.18.2.4 Waiver of Subrogation: The Agency and Contractor waive all rights against (1) each other and any of their subcontractors, sub-subcontractors, agents and employees, each of the other, for damages caused by fire or other causes of loss to the extent the property insurance provided by the Contractor pursuant to this Section 3.18.2 covers and pays for the damage, except such rights as they have to proceeds of such insurance held by the Contractor. The Agency or Contractor, as appropriate, shall require of the subcontractors, sub-subcontractors, agents and employees, each of the other, by appropriate written agreements, similar waivers each in favor of other parties enumerated herein. The policies shall provide such waivers of subrogation by endorsement or otherwise. A waiver of subrogation shall be effective as to a person or entity even though that person or entity would otherwise have a duty of indemnification, contractual or otherwise, did not pay the insurance premium directly or indirectly, and whether or not the person or entity had an insurable interest in the property damaged.

3.19 Performance and Payment Bonds: Prior to beginning work on a Delivery Order, the Contractor shall deliver to the Agency a Performance Bond and a Labor & Material Payment Bond if the Contractor’s agreed upon compensation for the Work of the Delivery Order exceeds $50,000 or the Agency requests such bonds. Each bond shall be in the amount of 100% of the amount of the Delivery Order. The Contractor’s Performance Bond shall be in the form of the SE-355, Performance Bond, and the Labor & Material Payment Bond shall be in the form of the SE-357, Labor & Material Payment Bond. The surety company providing the Bonds shall have, at a minimum, a “Best Rating” of “A” as stated in the most current publication of “Best’s Key Rating Guide, Property - Casualty.” Contractor’s failure to provide bonds as herein required shall be an event of default justifying the Agency, in its sole discretion, in terminating this Contract for cause.

3.20 Shop Drawings and Samples:

3.20.1 Contractor shall prepare or cause to be prepared shop drawings for fabricated items. Shop drawings shall consist of drawings, diagrams, illustrations, schedules, brochures, and other data which are prepared by the Contractor, sub-Contractor, manufacturer, supplier, or distributor and depict that portion of the work. Shop drawings shall be submitted, reviewed, and approved by the Contractor prior to submitting to the Agency and A/E. Shop drawings approved by the Contractor shall bear a stamp denoting that they have been review and are “approved” or “approved as noted” or similar designation. Contractor shall submit the number of sets as specified in the Delivery Order plans or specifications or in the absence of a specification submit enough copies for the Agency to retain two copies plus the number desired to be returned to the Contractor. The Agency and A/E will review the shop drawings with reasonable promptness but only for conformity with the design.

3.20.2 Contractor shall submit samples as required by the Delivery Order. Samples are physical examples furnished by the Contractor of sufficient size and quantity to provide a good representation of the material proposed to be installed. Samples submitted will not be returned unless requested by Contractor and agreed to by the A/E. The Contractor shall pay shipping costs. The final installed product shall match the approved sample.

3.21 Inspection and Testing of Materials:

3.21.1 The Contractor shall leave uncovered all areas of work that will be covered that are called out in the construction documents to be left uncovered, or the Agency or A/E requests to be left uncovered prior to being inspected. The Contractor shall give adequate notice to the Agency and A/E of the time requested for an inspection of areas to be covered.

3.21.2 If the Contractor covers areas that were to be left uncovered, the Contractor shall cause the area to be uncovered for inspection. After being inspected, the Contractor shall repair the area with craftsmen skilled in the appropriate trades needed for the repair at no additional cost to the Agency.

3.22 Substitutions:

3.22.1 The Contractor shall submit proposed substitutions to the Agency for the Agency’s approval prior to execution of each Delivery Order.

3.22.2 Reference in the Contract Documents to a designated material, product, thing, or service by specific brand or trade name followed by the words “or equal” and “or approved equal” shall be interpreted as establishing a standard of quality and shall not be construed as limiting competition. The Contractor may use the products of other another manufacturer’s provided it is an ‘approved equal’ that meets or exceeds the specification for the specified product. The Contractor must submit adequate information about the product to show that the submitted product meets the level of quality as the product specified.

3.22.3 The Contractor shall not substitute any product, article, appliance, equipment, or material that is specified without prior written approval of the Agency.

3.23 Receiving and Storing Materials and Equipment: The Contractor shall have an authorized person or persons to receive all items delivered to the site of the Work and shall properly unload, check for completeness of shipment, and in-transit damage. The Contractor shall properly handle and store materials, supplies, equipment etc. in accordance with the contract documents or manufacturer’s printed instructions for each product.

3.24 Schedule and Reports: Promptly after the Agency issues a Delivery Order, the Contractor shall present a construction schedule in a form satisfactory to the Agency. At intervals agreed upon in the Delivery Order, the Contractor shall update the schedule showing the actual progress of the work and adjustment in completion dates. If the work falls behind schedule, the Contractor shall present a plan for completion of the work by the scheduled date for completion.

3.25 Time for Completion:

3.25.1 Each Delivery Order signed by the Agency and Contractor shall set forth the time for completion of the Work specified therein. Contractor shall make a request for extension of time within seven days of the event giving rise to the request. The Contractor shall adequately document delays of the work that are due to circumstances beyond the control of the Contractor and shall submit the documentation to the Agency with any request for an extension. In the event of ongoing delay, the Contractor shall notify the Agency in its request for an extension of time that the cause of delay is ongoing. In such case, the Contractor shall supplement its request the cause of delay ends or the project is completed, whichever is sooner.

3.25.2 The Agency will review each request for time extension and equitably adjust the time for completion where (1) the event of delay actually impacted the critical path of the project and was beyond the control of the Contractor, and (2) completion of the Work was actually delayed.

1. CONTRACT ADMINISTRATION

4.1 Delivery Order - Cost Proposal: From time to time, the Agency will request a cost proposal for specific work and provide the Contractor adequate project information necessary to prepare a cost proposal. The Contractor shall prepare a cost proposal to complete the Work as requested. Unless specified by the Agency in its request, the cost proposal shall include the time frame for completion of the work. The Contractor shall submit the cost proposal to the Agency within one week of the request or as otherwise agreed upon by the Agency. The cost proposal shall be prepared according to the following method: *(Agency, check box that applies to this contract)*

Multiplier – Unless the Contractor proposes to provide work at a lower price, the Contractor shall use the multiplier, as bid, times the unit prices contained in the cost data guide specified in the contract documents, times the number of units of Work. The unit prices in the cost data guide include all labor, supervision, material, equipment, taxes, overhead (including but not limited to insurance, performance bond, and payment bond premiums), delivery, setup, installation, and profit. The Contractor may not add any additional mark-up to its price. If the Contractor chooses to subcontract some or all of the Work, the Contractor must still use its multiplier with the cost data guide for pricing the subcontracted work. However, if the work of the proposed Delivery Order is such that the Contractor may legally act as the sole prime Contractor under the licensing laws of this State and the subcontracted work (1) is outside the Contractor’s license; (2) is outside the license of any subcontractor listed in Section 7 of the bid; (3) is outside the scope of services covered by the Contract; and (4) does not exceed 20% of the total value of the work of the proposed Delivery Order, the Contractor may include a markup not to exceed 13% on the price of such subcontracted work. If the Contractor proposes not to use its multiplier and the cost data guide as the basis for the price of its work or subcontracted work, it must document that the proposed price is lower than the price would be if the Contractor used the multiplier and cost data guide.

Unit Prices – Unless the Contractor proposes to provide work at a lower price, the Contractor shall use the unit prices, as bid, times the number of units required for the Work to arrive at an extended price for that item of Work. The total of all extended prices becomes the Contractors price for the cost proposal. The unit prices include all labor, supervision, material, equipment, taxes, overhead (including but not limited to insurance), delivery, setup, installation, and profit. The Contractor may not add any additional mark-up to its price. If the Contractor chooses to subcontract some or all of the Work, the Contractor must still use the unit prices bid for pricing the subcontracted work. If the Contractor proposes not to use the unit prices bid as the basis for the price of its work or subcontracted work, it must document that the proposed price is lower than the price would be if the Contractor used the multiplier and cost data guide.

Low Bid – The Agency shall competitively bid the Work against all eligible Indefinite Delivery Contractors. The Delivery Order bid price shall include all labor, supervision, material, equipment, taxes, overhead (including but not limited to insurance), delivery, setup, installation, and profit. Under this pricing method, the Agency will award the Delivery Order to the lowest bidder.

4.2 Changes in the Work of a Delivery Order:

4.2.1 Any changes in the work must be approved by the Agency and executed by using the SE-695, Construction Services IDC Delivery Order Modification. The SE-695 must be signed by the Contractor and Agency. Except when the Delivery Order was awarded on the basis of competitive bids, the cost of any change order shall be calculated using the same method as pricing the Delivery Order.

4.2.2 In the absence of a total agreement concerning the item(s) for a change order, a Construction Change Directive shall be used.

* + 1. Agreed Overhead and Profit Rates:

For any adjustment to the Delivery Order for which overhead and profit may be recovered, other than those made pursuant to Unit Prices stated in the Contract Documents, the Contractor agrees to charge and accept, as full payment for overhead and profit, the following percentages of costs attributable to the change in the Work. The percentages cited below shall be considered to include all indirect costs including, but not limited to: field and office managers, supervisors and assistants, incidental job burdens, small tools, and general overhead allocations. The allowable percentages for overhead and profit are as follows:

.1 To the Contractor for work performed by the Contractor’s own forces, 17% of the Contractor’s actual costs.

.2 To each Subcontractor for work performed by the Subcontractor’s own forces, 17% of the subcontractor’s actual costs.

.3 To the Contractor for work performed by a subcontractor, 10% of the subcontractor’s actual costs (not including the subcontractor’s overhead and profit).

#### 4.3 Payments:

4.3.1 Contractor may submit monthly applications for payment for the Work of Delivery Orders scheduled to last two months or more in duration. Contractor shall submit only one application for payment for the Work of Delivery Orders scheduled to last less than two months in duration.

4.3.2 Delivery Orders Awarded by low bid: If the Contractor intends to submit more than one application for payment, the Contractor shall submit to the A/E, within ten days of Delivery Order award, a schedule of values allocating the entire Delivery Order Sum to the various portions of the Work and prepared in such form and supported by such data to substantiate its accuracy as the A/E may require. This schedule, unless objected to by the A/E, shall be used as a basis for reviewing the Contractor’s Applications for Payment. Contractor shall base its monthly applications for payment on work completed up to the date of the application using the approved schedule of values. The sum of all payments to the Contractor shall not exceed the agreed upon cost of the work set forth in the Delivery Order as adjusted by subsequent modifications to the Delivery Order, if any.

4.3.2 Contractor shall base its applications for payment on work completed up to the date of the application using the units of measure and prices contained in the *(Agency, check box that applies to this Contract)*

Unit price schedules in the cost data guide incorporated by the Contract Documents

Unit price schedule in Contractors bid.

4.3.3 Contractor’s applications for payment may include materials suitably stored on site for use in the Work provided the Contractor submits:

a. Proof of purchase & delivery;

b. Documentation showing the location of the material;

c. Certificate of insurance for the material with adequate coverage showing the Agency as the certificate holder.

4.3.4 The Agency will make payments to the Contractor for completed work based on the actual units or quantity of work completed. The Agency will make payments on the undisputed amounts of an application for payment within 21 days of receipt of the application.

4.3.5 Subcontractor Payments (Chapter 6 of Title 29 of the South Carolina Code of Laws, as amended): The Contractor shall pay each subcontractor no later than seven (7) days after receipt of payment from the Agency the amount to which the subcontractor is entitled, reflecting percentages actually retained from payments to the Contractor on account of the subcontractor’s portion of the Work. By appropriate agreement with its subcontractors, the Contractor shall require each subcontractor to make payments to Sub-subcontractors in a similar manner.

4.3.6 If the Agency does not pay the Contractor within seven (7) days after the time established in Part 4.3.2 the undisputed amount of a payment request, then upon seven (7) additional days written notice to the Agency, the Contractor may stop the Work until the Contractor has received payment of the undisputed amount owing. The Contract Time and the Contract Sum shall be equitably adjusted by the amount of the Contractor’s reasonable costs of shut down, delay and start-up, plus interest as provided for in the Contract Documents.

4.3.7 Retainage: The Agency, at its option, may withhold retainage as provided in S.C. Code Ann. § 11-35-3030(4).

4.3.8 Final Payment: Upon final payment by the Agency to the Contractor for the Work of a Delivery Order, all rights, title, and interest in and to all improvements and equipment constructed or installed on the premises shall vest in the Agency at no additional cost, free and clear of all any liens and encumbrances created or caused by the Contractor.

4.3.9 Withholding of Payments: Payments may be withheld to the extent of, and on account of (1) defective Work not remedied, or Work not performed in accordance with the Contract Documents; (2) claims filed by third parties; (3) failure of the Contractor to make payments promptly to the subcontractors for labor, materials, or equipment; (4) persistent failure to carry perform the Work in accordance with the Contract Documents; (5) failure by the Contractor to perform its obligations under the Contract Documents; or (6) a default by the Contractor under the Contract Documents. The Agency shall promptly notify the Contractor of any reason for withholding payment.

4.4 Delivery Order Completion and Closeout: Upon completion of all Work, the Contractor shall notify the Agency of its completion. The Agency shall schedule a Final Inspection and allow the Contractor to demonstrate that all equipment and systems operate as designed. The Agency may elect to have other persons, firms or agencies participate in the inspections. Projects exceeding the Agency’s construction procurement certification level shall require an inspection by the Office of State Engineer (OSE) and the State Engineer’s issuance of a Certificate of Occupancy. (The Contractor may find Agency construction certification limits on Procurement Services website at <http://procurement.sc.gov/PS/agency/PS-agency-audits.phtm>.) Final payment will not be due nor retained funds released until (1) the Agency agrees that the project is complete, (2) OSE or the Agency, which ever has authority, issues a Certificate of Occupancy, and (3) the Agency receives from the Contractor the following:

a. Affidavit of payment of debts and claims;

b. Consent of Surety, if any, to final payment.

1. **DISPUTES**

5.1 Both parties shall attemptto resolve disputes through good faith negotiations.

5.2 All disputes, claims, or controversies relating to the Contract, that cannot be resolved through good faith negotiations between the parties shall be resolved exclusively by the appropriate Chief Procurement Officer in accordance with Title 11, Chapter 35, Article 17 of the South Carolina Code of Laws, or in the absence of jurisdiction, only in the Court of Common Pleas for, or a federal court located in, Richland County, State of South Carolina. Contractor agrees that any act by the State regarding the Contract is not a waiver of either the State’s sovereign immunity or the State’s immunity under the Eleventh Amendment of the United States Constitution. As used herein, “the State” includes the Agency and the State Fiscal Accountability Authority.

5.3 Interest: Payments due to the Contractor and unpaid under the Contract Documents shall bear interest only if and to the extent allowed by Title 29, Chapter 6, Article 1 of the South Carolina Code of Laws. Amounts due to the Agency shall bear interest at the rate of one percent a month or a pro rata fraction thereof on the unpaid balance as may be due.

5.4 Contractor consents that any papers, notices, or process necessary or proper for the initiation or continuation of any claims or controversies relating to the Contract; for any court action in connection therewith; or for the entry of judgment on any award made, may be served on Contractor by certified mail (return receipt requested) addressed to Contractor at the address provided for the Contractor’s Representative or by personal service or by any other manner that is permitted by law, in or outside South Carolina. Notice by certified mail is deemed duly given upon deposit in the United States mail.

5.5 Continuation of Work: Pending final resolution of any dispute under this Contract, the Contractor will proceed diligently with the performance of its duties and obligations under the Contract Documents, and the Agency will continue to make payments of undisputed amounts in accordance with the Contract Documents.

1. LIMITATION OF LIABILITY

6.1 Notwithstanding any other provision of the Contract Documents, but subject to a duty of good faith and fair dealing, the Contractor and Agency waive Claims against each other for listed damages arising out of or relating to this Contract. This mutual waiver includes

6.1.1 For the Agency, listed damages are (i) lost revenue and profit, (ii) losses resulting from injury to business or reputation, (iii) additional or escalated overhead and administration expenses, (iv) additional financing costs, (v) costs suffered by a third party unable to commence work, (vi) reasonable attorney’s fees, (vii) any interest, except to the extent allowed by Part 5.3 (Interest), (viii) lost revenue and profit for lost use of the property, (ix) costs resulting from lost productivity or efficiency, and (x) damages incurred by the Agency for rental expenses, for losses of use, income, profit, financing, business and reputation, and for loss of management or employee productivity or of the services of such persons; and

6.1.2 For the Contractor, listed damages are (i) lost revenue and profit, (ii) losses resulting from injury to business or reputation, (iii) additional or escalated overhead and administration expenses, (iv) additional financing costs, (v) reasonable attorney’s fees, (vi) any interest, except to the extent allowed by Part 5.3 (Interest); (vii) unamortized equipment costs; and (viii) losses incurred by subcontractors for the types of damages the Contractor has waived as against the Agency.

6.2 This mutual waiver is applicable, without limitation, to all listed damages due to either party’s termination in accordance with Part 9. Nothing contained in this Part 6 shall be deemed to preclude an award of liquidated damages, when applicable, in accordance with the requirements of the Contract Documents. This mutual waiver is not applicable to amounts due or obligations under Part 3.17 (Indemnification).

1. **Hazardous Materials**

7.1 Contractor’s Responsibilities With Respect to Hazardous Materials: The scope of Work the Contractor is to perform pursuant to this Contract excludes any work or service of any nature associated or connected with the discovery, identification, abatement, cleanup, control, or removal of any currently existing Hazardous Materials or Mold on, in, or nearby the site of the Work. When requesting cost proposals, the Agency will identify known Hazardous Materials or Mold on, in, or nearby the site of the Work. The Agency agrees that all duties and obligations in connection with any Hazardous Materials or Mold currently located in, on or nearby the Site or brought into the Site by a party other than the Contractor or its subcontractors, other than those defined in the Delivery Order for the Work affected by the Hazardous Material or Mold, are not the Contractor’s responsibility. Should the Contractor become aware, discover or based on reasonable evidence suspect the presence of Hazardous Materials or Mold beyond those addressed in the Delivery Order for the Work affected by the Hazardous Material or Mold, the Contractor will immediately cease work in the affected area, and will promptly notify the Agency of the conditions discovered. Should the Contractor stop work because of such discovery or suspicion of Hazardous Materials or Mold, then the Contract Time will, should the Agency elect to choose to continue the Work after remedy thereof, be reasonably extended by Change Order to cover the period required for abatement, cleanup, or removal of the Hazardous Materials or Mold. The Contractor will not be held responsible for any claims, damages, costs, or expenses of any kind associated with such period during which work has been stopped as a result of Hazardous Materials or Mold.

7.2 Hazardous Materials Introduced to the Site by Contractor: If the Contractor, its subcontractors, and any party for whom they may be liable, introduces any Hazardous Materials to the Site then the Contractor, at its sole cost and expense, shall be responsible for any response, removal, cleanup, and/or other remedial action required by applicable law. If any Mold occurs within the Site as the result of the negligent implementation of the Project or the improper functioning of the Conservation Measures, then the Contractor, at its sole cost and expense, shall be responsible for any response, removal, cleanup, or other remedial action required by applicable law. Except as to the Contractor’s initial response to an emergency, any such remedial action(s) shall require the prior review and approval of the Agency.

1. MISCELLANEOUS PROVISIONS

8.1 Governing Law: This Contract shall be governed by the laws of South Carolina, except its choice of law rules.

8.2 Severability: If any provision of this Contract shall be held to be invalid, illegal, or unenforceable, the validity, legality and enforceability of the remaining provisions shall not be affected or impaired thereby.

8.3 No Waiver: No course of dealing or failure of the Agency and/or the Contractor to enforce strictly any term, right or condition of this Contract shall be construed as a waiver of such term, right or condition. No express waiver of any term, right, or condition of this Contract shall operate as a waiver of any other term, right, or condition.

8.4 Rights Cumulative: Except as otherwise provided in this Contract, (i) rights and remedies available to the Agency and/or the Contractor as set forth in this Contract shall be cumulative with and in addition to, and not in limitation of, any other rights or remedies available to the Parties at law and/or in equity, and (ii) any specific right or remedy conferred upon or reserved to the Agency and/or the Contractor in any provision of this Contract shall not preclude the concurrent or consecutive exercise of a right or remedy provided for in any other provision hereof.

8.5 Notices: Any notices required to be given under this Contract shall be in writing and shall be delivered either by (i) certified mail, return receipt requested, in which case notice shall be deemed delivered three (3) business days after deposit, postage prepaid, in the U.S. mail; (ii) a reputable messenger service or a nationally recognized overnight courier, in which case notice shall be deemed delivered one (1) business day after deposit with such messenger or courier; or (iii) personal delivery with receipt acknowledged in writing, in which case notice shall be deemed delivered when received. All notices shall be sent to the representatives identified in the Part G of the Agreement at the addresses provided therein. The foregoing addresses may be changed from time to time by notice to the other Party in the manner herein provided for.

8.6 Economic Conflict of Interest: A Contractor shall not have or exercise any official responsibility regarding a public contract in which the Contractor, or a business with which he is associated, has an economic interest. A person working for Contractor shall not have or exercise any official responsibility regarding a public contract in which the person, an individual with whom he is associated, or his family members have an economic interest. If Contractor is asked by any person to violate, or does violate, either of these restrictions, Contractor shall immediately communicate such information to the Agency Representative. The State may rescind, and recover any amount expended as a result of, any action taken or contract entered in violation of this provision. The terms “business with which he is associated,” “economic interest,” “family member,” “immediate family,” “individual with whom he is associated,” “official responsibility” and “person” have the meanings provided in S.C. Code Ann. § 8-13-100.

8.7 Illegal Immigration: Contractor certifies and agrees that it will comply with the applicable requirements of Title 8, Chapter 14 of the South Carolina Code of Laws and agrees to provide to the State upon request any documentation required to establish either: (a) that Title 8, Chapter 14 is inapplicable both to Contractor and its subcontractors or sub-subcontractors; or (b) that Contractor and its subcontractors or sub-subcontractors are in compliance with Title 8, Chapter 14. Pursuant to Section 8-14-60, “A person who knowingly makes or files any false, fictitious, or fraudulent document, statement, or report pursuant to this chapter is guilty of a felony and, upon conviction, must be fined within the discretion of the court or imprisoned for not more than five years, or both.” Contractor agrees to include in any contracts with its subcontractors language requiring its subcontractors to (a) comply with the applicable requirements of Title 8, Chapter 14, and (b) include in their contracts with the sub-subcontractors language requiring the sub-subcontractors to comply with the applicable requirements of Title 8, Chapter 14. (An overview is available at [www.procurement.sc.gov](http://www.procurement.sc.gov))

8.8 Drug-Free Workplace: The Contractor certifies to the Agency that Contractor will provide a Drug-Free Workplace, as required by Title 44, Chapter 107 of the South Carolina Code of Laws, as amended.

8.9 False Claims: According to the S.C. Code Ann. § 16-13-240, “a person who by false pretense or representation obtains the signature of a person to a written instrument or obtains from another person any chattel, money, valuable security, or other property, real or personal, with intent to cheat and defraud a person of that property is guilty” of a crime.

8.10 Non-Indemnification: Any term or condition is void to the extent it requires the State to indemnify anyone. It is unlawful for a person charged with disbursements of state funds appropriated by the General Assembly to exceed the amounts and purposes stated in the appropriations (§ 11-9-20). It is unlawful for an authorized public officer to enter into a contract for a purpose in which the sum is in excess of the amount appropriated for that purpose. It is unlawful for an authorized public officer to divert or appropriate the funds arising from any tax levied and collected for any one fiscal year to the payment of an indebtedness contracted or incurred for a previous year. (§ 11-1-40)

8.11 Enforcement and Interpretation of Building Codes: As required by Title 10, Chapter 1, Section 180 of the South Carolina Code of Laws, as amended, OSE shall determine the enforcement and interpretation of all building codes and referenced standards on state buildings. The Contractor shall refer any questions, comments, or directives from local officials to the Agency and OSE for resolution. When the amount of a Delivery Order exceeds the construction procurement certification of the Agency, the Contractor shall not commence the Work of the Delivery Order before receiving a copy of the Building permit issued by OSE. (The Contractor may find Agency construction certification limits on Procurement Services website at <http://procurement.sc.gov/PS/agency/PS-agency-audits.phtm>.)

8.12 Assignment: The Agency and Contractor respectively bind themselves, their partners, successors, assigns, and legal representatives to covenants, agreements and obligations contained in this Contract. Neither party to the Contract shall assign the Contract as a whole, or in part, without written consent of the other and then only in accordance with and as permitted by Regulation 19-445.2180 of the South Carolina Code of Regulations, as amended. If either party attempts to make such an assignment without such consent, that party shall nevertheless remain legally responsible for all obligations under the Contract.

8.13 Open Trade (Jun 2015): During the contract term, including any renewals or extensions, Contractor will not engage in the boycott of a person or an entity based in or doing business with a jurisdiction with whom South Carolina can enjoy open trade, as defined in SC Code Section 11-35-5300. [07-7A053-1]

1. SUSPENSION OR TERMINATION

9.1 Agency Right of Suspension: The Agency may, at any time, suspend the work, in whole or in part, with or without cause for such period of time as determined by the Agency. Except in the event of suspension due to a default of the Contractor, the contract sum will be equitably adjusted to reflect reasonable costs actually incurred by the Contractor due to delay or interruption resulting from such suspension.

9.2 Agency Right of Termination:

9.2.1 Termination for Cause: If the Contractor defaults, persistently fails or neglects to perform the Work in accordance with the Contract Documents, or fails to perform a provision of the Contract, the Agency shall provide written notice of such default, failure, or neglect to the Contractor. If the Contractor fails to cure such default, failure, or neglect within fifteen days from receipt of the Agency’s notice, the Agency may, without prejudice to any other right or remedy the Agency may have, terminate the Contract and take possession of the area at the Site affected by the Work.

9.2.2 Termination for Convenience: The Agency may, for its convenience, terminate all or any portion of the Work under an individual Delivery Order, or terminate this entire Contract, by ten (10) days written notice stating the effective date of the termination. Thereafter, the Agency shall pay the Contractor for Work actually performed before the date of termination. No payments shall be made for Work not actually performed, and no payment shall be made or due for lost profits on account of Work not performed.

9.3 Contractor Right of Termination:

9.3.1 The Contractor may terminate the contract, or Delivery Order, if work is stopped through no fault of the Contractor, or other persons performing work either directly or indirectly for the Contractor, for a period of time exceeding 60 consecutive calendar days due to a court order or other public authority having jurisdiction; or a Declared National emergency which requires the work to be stopped.

9.3.2 Agency Failure to Make Payment: Subject to the Agency’s right to withhold payments pursuant to Part 3.4.7, if the Agency fails to make payments to the Contractor as set forth in Part 10 and any other applicable provisions of the Contract Documents, the Contractor may, upon thirty (30) days’ prior written notice to the Agency, terminate the Contract and recover from the Agency payment for all Work performed and for proven loss with respect to materials, equipment, tools, and machinery, including reasonable overhead, profit and damages applicable to the Work for the Contract Services performed through the date thereof.