## Slide 1
Know Your
Construction Contracts:
A201 –
A Keystone Document
Linda A. Ciaccia RA NCARB
2023 OSE Facility Directors Conference

## Slide 2
It is adopted by reference in the Owner-Architect, Owner-Contractor, and Contractor-Subcontractor agreements = ‘keystone’ between the documents
Sets forth the rights, responsibilities and relationships of the Owner, Contractor and Architect, and provides terms and conditions under which all will work together during the construction process
The Architect participates in the preparation of the contract documents and performs construction phase duties, although not part of the Owner-Contractor agreement
Role of General Conditions:

## Slide 3
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 4
The Contract Documents
What are the Contract Documents?
Owner-Contractor Agreement
Conditions of the Contract
Drawings & Specifications
Addenda issued prior to execution of the contract
The Advertisement
Instructions to Bidders
Contractor’s Bid
Modifications made after execution of the contract -
  Change Orders
  Construction Change Directives
  Minor Changes in the Work
1 - General Provisions

## Slide 5
The Contract Documents
1 - General Provisions

## Slide 6
The Contract
What is the Contract?
The Contract Documents form the contract for construction and can be amended.
1 - General Provisions

## Slide 7
Contract Documents
What is the intent of the contract documents?
1 - General Provisions
To include all items necessary for the proper execution and completion of he work by the Contractor
The documents are complementary
In the event of ambiguities, the contractor shall provide better quality or greater quantity of work or comply with more stringent requirements, either or both, per Architect’s interpretation

## Slide 8
Notice to Proceed
What is established with the Notice to Proceed?
Notice to Proceed is issued by the Owner
SE-390 (D-B-B)
  Date of Commencement
  Contract Time
  Substantial Completion
  Liquidated Damages
Work with Contractor to establish dates
1 - General Provisions

## Slide 9
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 10
Owner’s Right to Stop Work
When does the owner have the right to stop work?
When the Contractor fails to correct Work and/or repeatedly fails to carry out the Work in accordance with the Contract Documents
Lapse in insurance coverage
2 - Owner

## Slide 11
Owner’s Right to Stop Work
2 - Owner

## Slide 12
Owner’s Right to Carry Out the Work
When does the owner have the right to
carry out the work?
If the Contractor defaults or neglects to carry out the Work in accordance with the Contract Documents and fails within a ten-day period after receipt of written notice
Owner can be reimbursed for expenses and Architect’s additional services
2 - Owner

## Slide 13
Owner’s Right to Carry Out the Work
2 - Owner

## Slide 14
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 15
Contractor & Applicable Codes
Is the contractor required to determine if the contract documents are in accordance with applicable laws and codes?
The contractor is not required to determine if the contract documents are in accordance with applicable laws and codes
If the contractor performs work knowing it to be contrary to applicable laws and codes, the contractor shall assume responsibility for such work and bear the costs to correct
Ask Architect for clarifications
3 - Contractor

## Slide 16
Substitutions
3 - Contractor
What are they and how are they handled?
Owner & Architect may, but not obligated to, consider only if in full compliance with specs
Burden is on the Contractor to show that it meets or exceeds spec; includes same warranty; cost is complete including all related costs for any adjustments to the design (not including Architect’s services), waives claim for added costs; meets any sustainability requirements (if required)
Owner to cover services for A/E work; can get reimbursement from Contractor

## Slide 17
Substitutions
3 - Contractor
What are they and how are they handled?

## Slide 18
Allowances
3 - Contractor
What are they and how are they applied?
Pre-determined amount of money for specific items (or group of items) that have not yet been selected or specified
Owner can delay making final decisions; typically finishes, equipment, hardware, etc.
Costs can be adjusted by Change Order
Not to be used as a substitute for items that typically fall under Contingency - unforeseen conditions, hazmat, etc. (Owner to protect funds in project budget for potential Contingency items)

## Slide 19
Allowances
3 - Contractor
What are they and how are they applied?

## Slide 20
Superintendent
3 - Contractor
What is their role and does the Owner has a say?
They represent the Contractor, and communications given to them shall be binding as if given to the Contractor
As soon as practicable after award of the contract (NOIA), shall notify the Owner and Architect of the name and qualifications
Within 14 days of receipt, Owner may notify if they have ‘reasonable’ objections; no notice constitutes no objection
Cannot be changed without Owner’s consent

## Slide 21
Superintendent
3 - Contractor
What is their role and does the Owner has a say?

## Slide 22
Construction Schedules
When provided and how often should construction schedules be updated?
The Contractor shall prepare and submit a construction schedule for the work promptly after being awarded the Contract
The schedule shall be updated at appropriate intervals as required by the contract
The pay application requires an updated construction schedule, per Owner & Architect
3 - Contractor

## Slide 23
Construction & Submittal Schedules
When provided and how often updated?
3 - Contractor
Contractor to maintain current construction and submittal schedules throughout the project

## Slide 24
Potential Workflow by PM
Once issue ‘Notice of Intent to Award’:
3 - Contractor
Finalize Superintendent – review & confirm (when ‘practicable’; required for O-C agreement)
Request Schedule – initial version should be provided; must be provided when submitting pay application (‘promptly’ after award; by reference – 14 days)
Request Subcontractor listing – review and comment within required timeframe (‘within 14 days after posting NOIA’)
Do not hesitate to ask for these items; the A201 requires them

## Slide 25
Shop Drawings, Product Data and Samples
What do Shop Drawings represent?
Shop Drawings and similar submittals are not Contract Documents
Their purpose is to demonstrate how contractor proposes to conform to the design concept and information provided in the Contract Documents
Shop drawings are reviewed and approved by the contractor prior to submitting to the architect for approval
3 - Contractor

## Slide 26
Fire Sprinkler Shop Drawings
Who prepares the Fire Sprinkler Shop Drawings and how are they submitted?
Prepared by a licensed sprinkler contractor; they shall certify the shop drawings and submit for review & approval
The architect’s engineer of record shall review, approve and submit to the State Fire Marshal for final review & approval
Prior to review by the State Fire Marshal (OSFM database), OSE to approve
3 - Contractor

## Slide 27
Indemnification
What is Indemnification?
To the fullest extent permitted by law, the Contractor shall indemnify and hold harmless the Owner, Architect, Architect’s consultants, and agents and employees from and against claims, damages, losses and expenses, including attorneys’ fees, resulting out of the performance of the Work, but only to the extent caused by the negligent acts or omissions of the Contractor or a Subcontractor
3 - Contractor

## Slide 28
Indemnification
3 - Contractor

## Slide 29
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 30
Administration of Contract
What is the Architect’s role during the construction phase of the project?
4 - Architect
Provide administration of the contract
Owner’s representative until the date that the final Certificate of Payment is issued
Have authority to act on behalf of the Owner only to the extent provided in the contract documents
Visit the site as necessary and keep Owner informed on the progress and quality of the portion of work completed

## Slide 31
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 32
Their Role
Who are they and does the Owner have a say?
5 - Subcontractors
Person or entity that has a direct contract with the Contractor
Within 14 days after posting NOIA, Contractor must notify Owner and Architect of the entities proposed for each principal portion of the work (incl. those on Bid form)
Within 14 days of receipt, Owner may notify Contractor with reasonable objection; no notice constitutes no reasonable objection
Contractor shall propose another; contract can be adjusted (sum and time)

## Slide 33
Their Role
Who are they and does the Owner have a say?
5 - Subcontractors

## Slide 34
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements
Table of Articles:

## Slide 35
Definition
6 - Construction by Owner or
Separate Contractors
Retained by the Owner under separate agreements
Can include work that is self-performed
Owner shall provide coordination of activities and the Contractor shall cooperate with them
Contractor can adjust schedule as required after a joint review / mutual agreement
Who are they? How is the Contractor affected?

## Slide 36
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 37
Impact of Changes
How are changes done & what is included?
7 – Changes in the Work
Changes in the work can be made without invalidating the rest of the contract
Change Orders must be agreed to by the Owner, A/E, and Contractor – work scope, time, cost
Change Directives must be agreed to by the Owner and A/E and may or may not by the Contractor; cost can be determined in multiple ways (lump sum, unit prices, cost/fee, etc.)
A/E may order minor changes that do not impact time or contract sum

## Slide 38
Impact of Changes
How are changes done & what is included?
7 – Changes in the Work
Overhead & Profit included
  Contractor’s forces not to exceed 17%
  Sub’s forces not to exceed 17%
  Contractor’s subs not to exceed 10%
Must provide itemized accounting (labor, materials & supplies incl. transportation, machinery rental, bonds & insurance, etc.)
Percentage can vary, depending on scope
Determine % prior to requesting change

## Slide 39
Impact of Changes
‘Pg2’ document:
7 – Changes in the Work
Can negotiate % with Contractor when requesting the change
When receive quote, verify correct % used

## Slide 40
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 41
Contract Time
How is Contract Time Defined and Changed?
8 - Time
Contract Time is from Date of Commencement to Substantial Completion
Contractor will complete the work on time and work cannot start prior to effective date of insurance and bonds
Time may be extended for changes or other delays that are not the contractor’s fault

## Slide 42
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 43
Requirements for Payment
What is included in this section?
9 – Payments and Completion
Contract sum
Schedule of Values
Applications for Payment
Certificate of Payment
Withholding Certification
Progress Payments Failure of Payment
Substantial Completion, Partial Occupancy

## Slide 44
Application for Payment
What is included & additional conditions?
Itemized application in accordance with the schedule of values, be notarized and reflect retainage
Can include equipment delivery & stored materials
Updated construction schedule
Contractor shall pay the Subcontractor within 7 days after receipt of payment
The owner can request written evidence from the contractor that subs have been paid
9 – Payments and Completion

## Slide 45
Application for Payment
What is included & additional conditions?
Payment by the Owner does not constitute acceptance of the Work
If the Architect does not certify the pay request within 7 days of issuance or if the Owner does not pay within 21 days of issuance, then the Contractor may, upon 7 additional days written notice, Stop Work until paid
9 – Payments and Completion

## Slide 46
Requirements for Completion
What is included?
9 – Payments and Completion
Substantial Completion - when the Owner can occupy/use the work area for its intended purpose
  Contractor requests & A/E inspects
  Owner releases retainage
Partial Occupancy - can be applied to a portion of the work
Final Completion & Final Payment - Contractor to request

## Slide 47
Acceptance of Nonconforming Work
How is nonconforming work accepted?
The Owner can accept work that is not in accordance with the Contract Documents
The Owner may do so instead of requiring its removal and correction
If correction required, Contract Sum will be reduced as appropriate and equitable
9 – Payments and Completion

## Slide 48
Final Completion and Final Payment
When is Final Completion achieved and
Final payment released?
If not agreed otherwise at Substantial Completion, Final Completion shall be within 30 days after Substantial Completion
Upon receipt of the Contractor’s written notice that work is ready for final inspection and receipt of the final pay request and final inspection has been performed
9 – Payments and Completion

## Slide 49
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 50
Safety
Who is responsible?
10 – Protection of
Persons and Property
Contractor is responsible for all safety precautions (typ. designates Superintendent)
Injury or Damage to Person or property - precautions shall be applied
Hazardous Materials – must notify Owner & Architect if unexpectedly encountered; Owner is responsible for remediation
Emergencies – Contractor to prevent damage, injury, loss; notify Owner & Architect

## Slide 51
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 52
11 – Insurance and Bonds
Coverage
Who is responsible?
Other documents include specific insurance requirements provided by each party per the various agreements (O-A, O-C, C-S)
Contractor shall buy and maintain insurance and bonds as specified; if lapse in coverage, Date of Commencement can be delayed
If Contractor’s insurance is cancelled/expired, can stop work until resolved, but changes to contract time and sum will not be adjusted

## Slide 53
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 54
12 – Uncovering and
Correction of Work
Responsibilities
How is it uncovering handled?
Contractor is responsible for making sure work remains visible (not covered) for any required inspections; will incur cost of uncovering / recovering
If Architect a requests uncovering that was not required initially, then Contractor entitled to adjustment in sum & time

## Slide 55
12 – Uncovering and
Correction of Work
Responsibilities
How are corrections handled?
Within 1 year of Substantial Completion shall be corrected promptly after receipt of notice that it is needed
If the Owner fails to notify the Contractor during that 1-year period, they waive the rights to require correction by Contractor
Contractor bears cost of any damage caused by the correction process

## Slide 56
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 57
13 – Miscellaneous Provisions
Tests & Inspections, Etc.
What is covered?
Tests & Inspections – Contractor to coordinate, Owner to pay
Owner's Materials – Contactor to store & protect; responsible for warranty & corrections
Interpretation of Codes – refer questions from local officials to Owner & OSE
Other Topics – Minority Business, Illegal Immigration, Drug Free Workplace, False Claims, Prohibited Act, Open Trade

## Slide 58
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 59
14 – Termination or Suspension
of the Contract
Termination & Suspension
When are these applied?
Termination by Contractor – if work is stopped, national emergency, nonpayment
Termination by Owner for Cause – not following CDs, not paying subs, not following codes/laws
Suspension by Owner for Convenience – can suspend for a period of time, but must adjust contract sum & time
Termination by Owner for Convenience – must pay for completed work; potentially can be reinstated

## Slide 60
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information
Table of Articles:

## Slide 61
Additional Cost & Time
What is included?
Continuing Contract Performance – Adjusting sum and time per Architect’s decisions; issue Certificates for Payment
Contractor not entitled to more time, if at fault for delays
Contractor & Owner to resolve disputes; Architect to assist Owner within defined timeframes
Further dispute resolution also included
15 – Claims and Disputes

## Slide 62
Weather Days
How many days of adverse weather are anticipated at the job site each month?
Conditions abnormal & documented and had an adverse affect on the schedule
Adverse weather for each month = 5 days
Contractor can claim additional days
Contractor must submit rain days with monthly pay request
Once reviewed & approved, will be included in next Change Order
15 – Claims and Disputes

## Slide 63
Delays
Provide detailed account of circumstances and dates that caused the delays
Contractor is not entitled to additional days for items that are concurrent or interrelated
Owner can require a revised construction schedule, including any additional affected activities
15 – Claims and Disputes
Can additional time be given?

## Slide 64
Table of Articles:
1 - General Provisions
2 - Owner
3 - Contractor
4 - Architect
5 - Subcontractors
6 - Construction by Owner or by Separate Contractors
7 - Changes in the Work
8 - Time
9 - Payments and Completion
10 - Protection of Persons and Property
11 - Insurance and Bonds
12 - Uncovering and Correction of Work
13 - Miscellaneous Provisions
14 - Termination or Suspension of the Contract
15 - Claims and Disputes
16 - Project Specific Requirements and Information

## Slide 65
16 – Project Specific
Requirements and Information
As required, by the Project
The A201 is not editable
Examples -
  List any clarifications or modifications to the existing text in the document
  List any additions, specific to the existing categories
  For CM-R project, list and attach ‘Standard Modifications to AIA A201-2017, SCOSE Version, CM-R Project’ (see Appendix C)