## Data Entry
Risk Analsysis Spreadsheet (to be used with Risk Analysis Framework)
Cause of Harm | Probability | Type of Harm | Consequence | Severity Rating | Risk Level | Mgmt. Approach | Mgmt. Mechanism | Cost of Mechanism
| Rare |  |  | Negligible | Very Low

## Lists
Probability | Severity Rating
Rare | Negligible
Unlikely | Low
Likely | Moderate
Almost Certain | High

## Example
Risks Associated with Third-Party Hosting of Patient Health Information
Cause of Harm | Type of Harm | Consequences
Lack of quick access to electronic records | Personal injury | Pay damages for personal injury
Data breach | Loss of client’s confidentiality / identity theft | Pay damages for privacy intrusion and identity theft monitoring, loss of trade secrets
Data breach, theft | Loss of reputation or public confidence | PR fees and associated costs
Losing access to proprietary application | Unusable data | Conversion costs or licensing fees
Data breach, theft | Loss of agency data | Replacement costs, costs for uploading soft or hard backup data
Service disruptions | Disrupted internal operations | Loss of employee productivity, payment loss through rescheduled appointments
Risks Associated with Janitorial-Service Contracts
Cause of Harm | Type of Harm | Consequences
Wet floors, unsecured tools and equipment, use of toxic or allergenic cleaning products, unvaccinated cleaning staff, etc. | Personal injury to agency staff | Compensation for personal injury, loss of employee productivity, etc.
Use of caustic or improper cleaning products, carelessness, vandalism, theft, accidental destruction, etc. | Property damage, loss of equipment or valuables | Replacement costs, loss of employee productivity, etc.
Breach of security | Loss of reputation or public confidence | Unquantifiable
Data breach, theft of papers, etc. | Loss of confidentiality | Compensation for invasion of privacy, loss of trade secrets, etc.
Risks Associated with Completing Software Development Projects
Cause of Harm | Type of Harm | Consequences
Delayed completion | Delay damages | Pay incumbent vendor for continued performance and software licensing fees (in addition to license fees for new service)
Project failure; non-completion | Costs of cover, re-procurement costs, sunk costs | Difference in price between failed contractor’s price and new vendor’s price, costs to re-procure new contract, the value of time and effort wasted on failed project, costly litigation

## Example 2
Cause of Harm | Probability | Type of Harm | Consequence | Severity Rating | Risk Level | Management Approach | Management Mechanism | Cost of Management Mechanism
Data breach, theft | Rare | Loss of agency data, loss of client confidentiality, loss of reputation | Replacement costs for back up data | High | Moderate | Mitigate, insure, and transfer | Mitigate by requiring a backup and requiring contractor to pay for identify theft protection; insure by requiring contractor’s insurance to cover sufficient risk; transfer by requiring contractor to indemnify claims by citizens against the agency | $________
(Optional)